# COMPREHENSIVE MIGRATION AND IMPLEMENTATION PLAN

Executive Summary

Goal: Migrate 2minutesermon.org to a modern, NextGen-style site using Webflow + Donorbox so the site looks and behaves like nextgenhopenetwork.org while keeping content editing simple, secure, and low maintenance. Outcome: A responsive, CMS-driven site with a hero and CTAs, impact stats, sermon feed and detail pages, donation flow, analytics, and editor training. Recommended approach: Rebuild in Webflow with structured CMS collections for sermons, series, team, events, and impact stats; embed Donorbox for donations; use a staging site and a short QA and training cycle.

Project Scope and Success Criteria

Scope

- Full site rebuild and redesign to match NextGen layout and visual language.

- CMS migration of all sermons, series, and static pages.

- Donation integration with recurring and one-time options.

- Forms, newsletter integration, analytics, SEO, and accessibility checks.

- Editor training and launch support.

Success Criteria

- Visual parity with NextGen on desktop and mobile.

- All sermons available in CMS with working video/audio/transcripts.

- Donation flow tested and live with receipts.

- Editors can add/edit sermons without breaking layout.

- 301 redirects in place and no major SEO loss.

Platform Recommendation and Why

Primary choice: Webflow + Donorbox

- Design parity: pixel-level control to reproduce NextGen hero, grids, and CTAs.

- CMS: structured collections for sermons, series, events, and team.

- Maintenance: hosted platform with SSL and automatic updates.

- Donations: Donorbox embeds provide recurring gifts, receipts, and easy integration.

- Editor experience: visual editor with role-based access and safe editing.

Alternate choice: WordPress (managed host) + GiveWP

- Choose only if you require advanced donor CRM, complex receipts, or many plugin integrations.

- Higher maintenance and security overhead.

Ordered Build Plan with Tasks and Deliverables

Phase 0 Prepare and Audit 2–4 days

- Deliverables: content inventory spreadsheet; access list; donation requirements doc.

- Tasks: inventory pages and sermons; collect logos, fonts, images; gather analytics and domain access; define donation flows and stakeholder approvers.

Phase 1 Information Architecture and Wireframes 3–5 days

- Deliverables: site map; annotated wireframes; CMS field list.

- Tasks: map NextGen sections to pages; create wireframes for Home, Sermon list, Sermon detail, Donate, About, Team, Events; finalize design tokens.

Phase 2 CMS Schema and Content Model 1–2 days

- Deliverables: CMS collections created and approved.

- Collections: Sermons, Series, Pages, Team, Events, Impact Stats.

- Editor roles: Admin, Editor, Contributor.

Phase 3 Design and Build in Webflow 7–14 days

- Deliverables: staging Webflow site with templates, CMS, and donation embed.

- Tasks in order: set global styles; build header/footer; build Home hero and impact grid; create CMS collections and templates; build sermon list and detail templates; add forms and newsletter; embed Donorbox; responsive adjustments; SEO metadata.

Phase 4 Content Migration and Import 2–5 days

- Deliverables: sermons imported; media optimized; redirects list.

- Tasks: prepare CSV; optimize images/audio; bulk import sermons; manual QA on sample items; create 301 redirects.

Phase 5 QA Accessibility and Testing 2–4 days

- Deliverables: QA report and fixes applied.

- Tasks: test forms, donation flow, video/audio playback, search and filters; run accessibility checks; performance tuning; cross-browser testing.

Phase 6 Training and Launch 1–3 days

- Deliverables: training notes/recording; launch checklist completed.

- Tasks: editor training session; final content freeze; DNS switch to Webflow; monitor first 72 hours.

Post Launch Ongoing

- Deliverables: monthly analytics report; quarterly accessibility audit.

- Tasks: content updates, donation monitoring, backups, SEO reviews.

CMS Schema and CSV Mapping

Collections and key fields

| Collection | Key Fields | Purpose |
| --- | --- | --- |
| Sermons | Title; Slug; Date; Preacher; Series ref; YouTube URL; Audio URL; Transcript; Tags; Featured image; Excerpt; SEO fields | Sermon detail template |
| Series | Title; Slug; Description; Cover image; Related sermons | Group sermons |
| Pages | Title; Slug; Hero image; Body; SEO fields | About, Ministries, Donate |
| Team | Name; Role; Bio; Photo; Social links | Staff page |
| Events | Title; Date/time; Location; Registration link; Image | Events listing |
| Impact Stats | Number; Label; Icon; Short description | Home impact grid |

CSV field mapping for Sermons

| CSV Column | Example | Webflow Field |
| --- | --- | --- |
| title | The Power of Small Steps | Title |
| slug | power-of-small-steps | Slug |
| date | 2026-07-01 | Date |
| preacher | Pastor Joe | Plain text |
| series | Summer Series 2026 | Reference |
| youtube_url | https://youtu.be/abcd1234 | Embed/URL |
| audio_url | https://cdn.example.com/audio.mp3 | File URL |
| transcript | Full transcript text | Rich text |
| tags | faith;discipleship | Tags |
| featured_image | image-file.jpg | Image |
| excerpt | Short summary | Plain text |
| seo_title | Power of Small Steps sermon | SEO title |
| seo_description | Short SEO description | SEO description |

Donation Integration Details

Recommended provider: Donorbox embed for Webflow.

- Why: fast setup, recurring gifts, donor receipts, embeddable modal or inline form.

- Integration steps: create Donorbox campaign; copy embed code; place embed in hero CTA and Donate page; test one-time and recurring flows; connect Donorbox to Mailchimp or CRM via Zapier if needed. Advanced option: Stripe Checkout for simple payments or Memberstack/Outseta for memberships.

Timeline and Cost Estimates

| Phase | Time | Estimated Cost Range |
| --- | --- | --- |
| Audit and planning | 2–4 days | $0–$500 internal |
| Wireframes and IA | 3–5 days | $300–$1,200 |
| Design and build Webflow | 7–14 days | $1,200–$6,000 |
| Content migration | 2–5 days | $200–$1,000 |
| QA and testing | 2–4 days | $200–$800 |
| Training and launch | 1–3 days | $150–$600 |
| Hosting and integrations annual | ongoing | Webflow hosting $300–$1,200; Donorbox fees variable |
| Total timeline | 2–6 weeks | Total build cost $2,150–$9,300 |

Cost drivers

- Custom animations and advanced search increase cost.

- Agency builds cost more than freelancers or DIY.

- WordPress alternative adds plugin maintenance and security costs.

Migration Checklist Ordered

- Complete content inventory CSV for all pages and sermons.

- Choose platform and purchase Webflow CMS plan.

- Create Webflow project and set global styles.

- Build CMS collections and templates.

- Create Home, Sermon list, Sermon detail, Donate, About, Team, Events pages.

- Prepare and optimize media assets.

- Import sermons via CSV and verify embeds.

- Embed Donorbox and test donation flows.

- Implement SEO metadata and structured data for sermons.

- Create 301 redirects from old URLs to new URLs.

- Run QA and accessibility checks and fix issues.

- Train editors and perform final content freeze.

- Update DNS and go live.

- Monitor analytics and donation conversions for 72 hours.

QA, SEO, Accessibility and Analytics Checklist

- Accessibility: alt text for images; color contrast >= 4.5:1 for body text; keyboard navigation; transcripts for videos.

- SEO: meta titles and descriptions; Open Graph images; sitemap; structured data for sermons.

- Analytics: install Google Analytics 4; set donation conversion events; add Facebook Pixel if used.

- Performance: lazy load images; compress media; test Lighthouse scores.

- Security: enable 2FA for editors; strong passwords; Webflow SSL.

Risks and Mitigation

- Risk: Donation receipts or CRM needs exceed Donorbox capabilities. Mitigation: Integrate Donorbox with a donor CRM via Zapier or choose WordPress + GiveWP.

- Risk: Editors accidentally break layout. Mitigation: Use Webflow Editor roles and provide a short style guide and training.

- Risk: SEO traffic loss. Mitigation: Implement 301 redirects and preserve URL structure where possible; monitor Search Console.

Roles and Responsibilities

- Project Owner: approves design and content, provides access.

- Designer/Developer: builds Webflow site, CMS, and donation embed.

- Content Lead: prepares CSV, optimizes media, verifies transcripts.

- Editor(s): add new sermons and pages after training.

- QA Lead: runs accessibility, performance, and functional tests.

Yes — I’ve looked at both sites and it’s doable. We can rebuild the site in Webflow so it looks and behaves like NextGen, and do it without any coding so nontechnical people can edit it easily. All sermons, videos, and transcripts will be moved into a CMS so you can add new content without touching code. We’ll also add a proper donation solution (Donorbox or Stripe) that supports one-time and recurring gifts and issues receipts if you need them. Because you already have content, the CMS (Content Management System) is essential, and if you have donors we’ll set up donor handling and reporting so gifts and receipts are tracked properly. As it stands, I am guessing it might take 5+ weeks depending on how much content needs migrating. We’ll look up Webflow costs once we finalize the plan and decide to proceed!

What I need to look into:

Immediate Next Steps (what to do now)

- Confirm platform: reply “Webflow + Donorbox” to proceed.

- Share content inventory: upload or paste a list of pages and sermons or request the CSV template.

- Provide access: domain registrar, Google Analytics, YouTube channel, and any donation accounts.

- Decide budget and timeline: confirm whether you want DIY, freelancer, or agency build.

Deliverables I will produce if you confirm

- Ready-to-fill CSV template for sermons and series.

- One-page Webflow build checklist with exact component specs and class name suggestions.

- Page-by-page wireframe PDF-style spec in chat format you can hand to a builder.